## Sheet1
Organising a Track & Field Meet
Timeline | Tasks | Contacts
Well in advance -(6-9 months) | Within club, decide on provisional date and events. Get as many volunteers and officials from within your club as possible and confirm they are prepared to help.
| Contact ANI office with details of provisional arrangements and request for any support required eg extra officials, online entries etc. | Admin & Events Assistant info@athleticsni.org
Wait for approval of arrangements from ANI Competition Committee.
When approval is received -
Carry out risk assessment.
| Apply for permit from ANI. This will be pending until numbers of officials are confirmed. A provisional timetable must also be submitted with your permit | https://athleticsni.org/Permits
| Provisionally book the venue and first aid cover. | Proparamedics
Order numbers & pins. If required order medals/prize and field cards
6 weeks before event | If ANI officials are required, the timetable should be sent to ANI Officials Co-ordinator. | officials@athleticsni.org
Timetable to be sent to venue.
4 weeks before event | Confirm the timetable and publish it on social media/club website/ANI website etc.
| Entry system opens and should close 10 days before event. | Advice from Admin & Events assistant - info@athleticsni.org
10 days before event | Allocate athlete bib numbers.
Seed track athletes and complete lane draws.
Arrange procedure for results, live stream/live results/notice board print out.
5 days before event | Send final timetable, lane draws and athlete bib number to the photofinish team and announcer. | officials@athleticsni.org
Write/print field cards - two copies of each card.
Arrange for refreshments for officials. Tea/coffee biscuits for half day meeting. Lunch for full day meeting.
2 days before event | Arrange for venue electrical equipment to be charged. EDM for field events, TESS starting system, Walkie Talkies | Contact track manager.
Print out copy of the start lists for Announcer, Start Team, Photo Finish Team, Track Referee and Track Staff.
Day of event | Arrive early!
Display bib numbers, timetables, lane draws etc around the venue
Club volunteers to set up registration for athletes-Issue bib number and pins.
Have Walkie Talkie available for Meeting Organiser, First Aid, Announcer, Photo Finish, Starter, Track Referee, Field Referee, Results.
Have field cards ready for the Field Referee.
Set up Officials refreshment area.
Organise presentations if required. Work with announcer.
Organise results team. A volunteer should be available to display results on a notice board if this is the results method being used.
After meeting | Tidy up venue.
| Send results to ANI office as soon as possible. | shauna.bratten@athleticsni.org